## Slide 1: Construction Update Week 20 & 21
October 23rd to November 4th, 2017

## Slide 2: Progress Report Week 20
Installation of metal transition flashing over Blueskin rubber transition membrane
Brick nearing completion on West wall of gym /future sanctuary and storage room 113. Water penetration barrier installed over upper portion of block walls in preparation for installation of 127mm insulation.

## Slide 3: Progress Report Week 20
Thinking ahead! - framed openings for future make up air unit, exhaust fans and grease hood duct (fully complete above roof line complete with insulated curbs, temporarily insulated and capped with metal deck screwed on from bottom).
Installation of underground sanitary piping below storage room under future kitchen, capped below double doors to storage room

## Slide 4: Progress Report Week 20
A very busy construction area!
Installation of 127mm foam insulation at top of west wall of future sanctuary. Installation of vertical application of adhesive on backside provides space for moisture to discharge out of vertical secondary drainage plane to top of transition flashing.

## Slide 5: Progress Report Week 20
Brick and louvre installation complete at North wall of addition
Installation of shingles over self-adhering rubber membrane with rubber flashing at roof/concrete block wall transition. Also note plumbing vent terminal with orange test cap in place to prevent water entry until future commerical kitchen plumbing in completed

## Slide 6: Progress Report Week 20
Support of short trusses over storage rooms at concrete block wall
Plumbing vents roughed in for future commerical kitchen to behind future baseboard

## Slide 7: Progress Report Week 20
Test plug in place in attic plumbing vent in line cleanout installed adjacent to attic access to make future testing of drains, waste piping easy
Plumbing vent piping under pressure test

## Slide 8: Progress Report Week 20
Water penetration barrier complete over block wall, note also roof overflow with roof membrane extended through same
50mm spray in place foam insulation over plywood sheathing above soffit of storage room walls

## Slide 9: Progress Report Week 21
Work exterior wall water penetration barrier and insulation up to temporary opening in South wall of future platform
Masons completing final joint racking at Southwest corner, storage room 113

## Slide 10: Progress Report Week 21
127mm insulation in place with vertical drainage behind and water penetration barrier applied to concrete block wall. Also note, metal flashing over insulated wood curb and rubber membrane on lower roof.
127mm thick insulation in place ready for application of stucco finish, back-wrapped above metal flashing complete with gap for drainage

## Slide 11: Progress Report Week 21
127mm insulation in place with vertical drainage behind and water penetration barrier applied to concrete block wall. Also note, metal flashing over insulated wood curb and rubber membrane on lower roof.
Brackets to support hot galvanized ladder to upper roof installed with rubber membrane behind same

## Slide 12: Progress Report Week 21
Concrete block infill replaced with brick over existing rear entrance
Four of existing basement brick sills replaced with solid stone sill with rubberized flashing behind

## Slide 13: Progress Report Week 21
Parking lot lamp posts ready for installation
Existing paving removed at Northwest basement entry and drive

## Slide 14: Progress Report Week 21
Parking lot lamp posts ready for installation
Then there was light!!! parking lot lamps installed and working

## Slide 15: Volunteer Work
The freshen up of the basement level is well underway(Week 20) – Thanks to our volunteers!!!
A special thank you to Jonathan Molyneaux and Cora Millar for their organization of this work!!
Owen Brook, Ron Traviss, Tim Brook and Elisa Brook painting up a storm in the corridor leading to youth room

## Slide 16: Volunteer Work
The family team !! Stacy, Trent and Steve Favrin painting existing basement corridor
Allan Willms, Tom Millar, Tony Masi and Noah Masi the double tag team painting existing fellowship hall and corridor to washrooms

## Slide 17: Volunteer Work
The Irishman hard at work again!!!!! There is no stopping this fighting Irishman!!!! - Peter Carberry reinstalling wall louvre

## Slide 18: Other items from Week 20 and 21
Construction Site Meeting #9 held on October 26, 2017. Glenn Rienders, Mark Dykstra, Adrian van Eck, Les McComb and John Donato present.
Some items discussed:
EIFS colour and texture confirmed
Coping flashing colour confirmed
Pricing for spray-in-place foam insulation below gym/future sanctuary floor slab to replace proposed 2” board insulation and perminator radon barrier
Gas meter installation, roof drainage piping, preparation of elevator machine room discussed
Rear canopy design approved
Approved raised concrete patio roof walkways for service of HVAC units

## Slide 19: Other items from Week 20 and 21
Some items discussed and addressed in the past two weeks;
  Relocation of roof drainage piping in future platform area. Mechanical Engineer has re-designed this and quote for changes has been requested from Wellington.
  Updated construction estimate provided by CRD
  Concrete slab for lower bike rack to be located beside lampstand adjacent to concrete walk to city sidewalk
  Confirmation of main floor colour selections
  Gas piping, gas meter installation, reconnection of existing HVAC
  Approval of spray-in-place radon mitigation system received

## Slide 20: Next
Installation of EIFS (Exterior Insulation Finish System) will continue
Work on concrete walks will commence
Roof top HVAC units will be craned into place and installation of ductwork may begin
Re-installation of steeple
Barrier free lift installation (start of 3 to 4 week process)
Volunteers will continue with painting of existing rooms on the basement level